## Sheet1
Task | App | Assigned To | Priority | Target Date | Status
1. Map related
a. Direction - set destination by search | Mobile | Priyanka | 2
b. Direction arrow marks with speed and time at each mark | Mobile | Vijay | 2 |  | Not started
c. Course correction & multiple routes | Mobile | Priyanka | 2
d. Destination saving till the session end | Mobile | Vijay | 1 |  | Done but will change as map functionality changes
e. Map auto rotation | Mobile | Priyanka | 2
f. Feet by feet tracking | Mobile | Priyanka | 1
g. Automatic path when destination changes | Mobile | Priyanka | 2
2. Noise cancellation for locations – Algorithm implementation | Mobile | VR | 1
3. Health check | Mobile | Vijay | 1 |  | Not started
4. Locate – Use of Mini methods for performance | Mobile | VR | 1
5. Permanent Delete Profile & delete user | Mobile | Gopi | 1
6. Show ‘Switch on GPS’ in SOS, when SOS is on and GPS is OFF | Mobile | Vijay |  | Complete | Complete
7. Multi-profiles | Mobile | VR | 2
8. Facebook logout | Mobile | Vijay | 2 |  | In Middle/stuck
9. Exception handling in VMs | Mobile | Vijay | 3 |  | Not started
10. Privacy | Mobile | Gopi | 1
11. Security for global configurations | Mobile | VR
12. Sporadic slow app responsiveness when in 2G | Mobile | VR | 1
13. Group locations and send it once instead on every few sec to reduce traffic and save battery, to capture all possible locations | Mobile | VR | 1
14. Blocked users should not be allowed for addition | Mobile | Vijay | 1 |  | Not started
15. Keep Live when App in background | Mobile | VR | 1
16. Calling secured service methods | Mobile | VR/ Vijay | 1
17. MVVM to Local DB | Mobile | Vijay | 1 |  | Not started
18. Autosync when exiting – low priority | Mobile | Vijay | 2 |  | Not started
19. Release version history page | Mobile | Vijay | 2 |  | Not started
20. Live Tile for registered users | Mobile | Vijay | 1 |  | Not started
21. SOS image for Pin SOS to start screen feature | Mobile | Priyanka | 1
22. OS Bugs | Mobile | VR | 1
23. App Bugs | Mobile
a. Intermittently, single back button click exiting the user from app when user set gps first time, first time register | Mobile | Vijay | 1 | Complete | Complete
b. Sync button visibility issue | Mobile | Vijay / VR | 1
c. Retaining map view | Mobile | vijay | 1 | Complete | Complete
d. Retaining map destination in track me for a session | Mobile | vijay | 1 | Complete | Complete
e. Toast messagec & SOS Tile clicks | Mobile | Priyanka | 1
f. Add Buddy search, when results in no records, displaying msg and keeps on showing progress bar | Mobile | vijay |  | Complete | Complete
g. When tracking is ON and user is in main page, if phone locks for 5mins, it is not showing - Battery Saver | Mobile | Vijay | 1 |  | Not started
h. Privacy statement in FB App page | Mobile | Gopi | 1
i. First time app is loading in 2 secs. If exits and opens again, it is taking 15 secs | Mobile | VR | 1
j. Phone number Validate button to be available all the time (I remember you did it for a reason, not able to recall that) | Mobile |  | 2
K. In locate page in phone, the list is not ordered for SOS/Active/Inactive order | Mobile |  | 2
24. Retry Mechanism | Mobile | Vijay | 1 |  | In Middle
1. Security for services | Service | Sharath/ Rajesh/ Navin
a) PoC to get headers in WCF | Service | Rajesh | 1 | Complete | Complete
b) Implement headers PoC in SOS.RESTService and call a dummy method for authentication | Service | Navin | 1 | Complete | Complete
c) Implement the authentication in dummy method created above | Service | Sharath | 1 |  | In Progress
2. Group onboarding with group registration page in portal | Service | Sharath | 2
3. Update in encryption logic for performance and more security | Service | Navin | 2
4. Mini method of Locate Buddy – Phone | Service | Sharath | 1
5. Optimize for Portal | Service | Sharath | 1
6. Optimize Worker role for transactions | Service | Navin | 1
7. Archiving to Skydrive/ purging | Service | Sharath | 3
8. Phone Number in PhoneValidation encryption. Buddy email encryption? | Service | Navin/ Rajesh
9. Send SMS/email to buddy while a buddy add that he can track the user and with two links ‘Unsubscribe’ and ‘Block’. If he wish not to receive msgs for that user, unsubscribe for receive msgs by that buddy for a profile. He can also block the profile for further addition | Service | Sharath/ Rajesh
10. Method to capture multiple locations at once | Service | Sharath
11. Worker role changes for scaling and performance | Service | Navin
12. Date and Time management – Localization | Service | Rajesh
13. Bugs | Service
a. Primary Buddy returning false in UpdateProfile | Service | Rajesh
14. Review the workflow for any potential loopholes which can put devices to an orphaned state | Service | Sharath/Rajesh | 1
1. Login pending task, including fixing workflow | Portal | Manoj | 1
2. Group registration | Portal | Ram | 2
3. UI has to be changed for accordions - Can we introduce Modern UI, in place of accordions? | Portal | Shri | 2
4. UI bottom looking like some incomplete page. Needs fix | Portal | Ram | 1
5. Heat map and Evidence display for incidents | Portal | Shri | 2
6. Page with Unscubscribe and Block functionalities | Portal | Surender | 1
7. Calling secured service methods | Portal | Surender | 1
8. Show direction marks with speed and time at each mark | Portal | Surender | 1
9. Bugs | Portal | Ram | 1
10. After image is opened from portal, most of the times, the page hangs | Portal | Ram | 1